## Slide 1: EOTs and Omicron
Legal Overview
Arie Moore │ Director

## Slide 2: Overview
Omicron environment
Contract position
Delay and disruption
  Assessing effects
  Approaches to measure
  Claiming EOTs

## Slide 3: Omicron environment
Changing situation
More isolation requirements
Less ‘lockdown’ situations
10% - 20% of workforce isolating across businesses

## Slide 4: Contract position
Three categories of projects
  Pre-2020 contracts
  ‘COVID clause’ contracts
  New projects
Typically treated as a variation, meaning:
  Entitlement to be granted EOT
  (Costs paid but no allowance for profit)

## Slide 5: Contract position
Lockdowns easy to assess
Omicron effects: absence / fewer workers
NZS 3910 covers disruption costs:
  (b) Loss of productivity; where the flow of particular work is interrupted, and the workforce loses continuity and has to rebuild its maximum performance.
Substantiation more challenging

## Slide 6: Delay and disruption
  Omicron effects more associated with disruption
  Measuring effect on progress of works
    Number of absences from site
    Effect on progress
    Increases in cost

## Slide 7: Delay and disruption
  Assessing disruption
    Productivity based
    Cost based
  Measured mile analysis
  Earned value analysis
  Programme analysis

## Slide 8: Delay and disruption
  What is the ‘event’ of delay
  Continuing effects
  NZS 3910 approach:
    More than one notice (monthly)
    Each claiming a specific period of extension

## Slide 9: Thank you
Arie Moore Director
E arie@reflectivelaw.co.nz
M 027 457 9203

## Slide 10
CONSTRUCTION SECTOR ACCORD
A high performing construction sector for a better New Zealand
COVID-19 Risk Management
April 2022

## Slide 11
COVID-19 Risk Management
Set of tools and principles to follow in managing COVID-19 related risks
Focused on contractual arrangements between public sector agencies and contractors
Principles may be adopted by private sector and other contracting parties

## Slide 12
COVID-19 Risk Management
Principles of good risk management
Who is best placed to manage COVID-19 risk?
A focus on early engagement and collaboration
Roles of the project team in managing COVID-19 risk
Specific 3910 clauses needing revision
Example COVID-19 Clause

## Slide 13
Who is best placed to manage COVID-19 risk?
neither the contractor or client can predict or control the impact of COVID-19
good practice to allocate risks to the party best able to manage
recommended that agencies retain the risk of the impacts of COVID-19
for in flight projects recommended that public and private sector adopt principles
Why?
avoid excessive risk allowances for time and cost at tender stage
reduce the risk of second order consequences for the project

## Slide 14
What is a fair and reasonable position in managing COVID-19 Risk?
The Accord View | NZS 3910 Provisions
Impacts of COVID-19 are not always in control of contractor | Impacts should be treated as a variation, and valued in accordance with Clause 9.3. Net effect of variations under 10.3.1 are grounds for extension of time
Main contractor: in control of works best placed to advise on potential impacts on programme and cost | Clause 5.21.1 - Contractor should notify the Engineer of a COVID-19 impact as soon as it becomes aware it may alter the Contract Price and/or completion date
Parties should work together in a spirit of collaboration and co-operation | Clause 5.21.2 - Contractor should request a meeting with the Engineer and they should work together to explore proposals for reducing impacts
Try to mitigate risks and issues on no surprises basis | Clause 5.21.3 - Any failure by the Contractor to give advance notification can be taken into account by the Engineer in valuing any entitlements to extension of time and costs

## Slide 15
Example of Special Condition to address COVID-19 Time and Cost Risk through NZS 3910:2013
9.6 Covid Variation
9.6.1 If during the Contract a Covid Impact occurs, then, the Covid Impact shall be treated as a Variation, subject to this 9.6.
9.6.2 This 9.6 represents the Contractor’s sole remedy in respect of Covid and any Covid Impact. The Contractor shall have no right to make any claim (whether for time, Cost, Variation or otherwise) in respect of Covid and any Covid Impact under any other provision of the Contract or at law.

## Slide 16
Example of Special Condition to address COVID-19 Time and Cost Risk through NZS 3910:2013
9.6.3 If a Covid Impact occurs, then the Contractor shall:
(a) Keep the Principal informed at all times (and on request) of the likely effect of the Covid Impact and the value of the Covid Variation;
(b) Work collaboratively with (and meet and consult with) the Principal and the Engineer to:
(i) Explore proposals for avoiding or reducing (including by innovation) the Covid Impact’s effect on the Contract Works, the Contract Price or the programme; (ii) Minimise the Covid Impact’s effect on Subcontractors and the Contractor’s supply chain; and
(c) To the extent possible, obtain the approval of the Engineer prior to incurring or committing to any Cost due to a Covid Impact.

## Slide 17
Example of Special Condition to address COVID-19 Time and Cost Risk through NZS 3910:2013
9.6.4 Subject to 5.21.3 (if applicable), the value of a Covid Variation shall as far as possible be valued by agreement between the Contractor and the Engineer. Failing agreement, the value shall be determined by the Engineer in accordance with 9.3.

## Slide 18
Example of Special Condition to Address COVID-19 Time and Cost Risk through NZS 3910:2013
9.6 Covid Variation
9.6.1 If during the Contract a Covid Impact occurs, then, the Covid Impact shall be treated as a Variation, subject to this 9.6.
9.6.2 This 9.6 represents the Contractor’s sole remedy in respect of Covid and any Covid Impact. The Contractor shall have no right to make any claim (whether for time, Cost, Variation or otherwise) in respect of Covid and any Covid Impact under any other provision of the Contract or at law.
9.6.3 If a Covid Impact occurs, then the Contractor shall:
(a) Keep the Principal informed at all times (and on request) of the likely effect of the Covid Impact and the value of the Covid Variation;
(b) Work collaboratively with (and meet and consult with) the Principal and the Engineer to:
(i) Explore proposals for avoiding or reducing (including by innovation) the Covid Impact’s effect on the Contract Works, the Contract Price or the programme; and
(ii) Minimise the Covid Impact’s effect on Subcontractors and the Contractor’s supply chain; and
(c) To the extent possible, obtain the approval of the Engineer prior to incurring or committing to any Cost due to a Covid Impact.
9.6.4 Subject to 5.21.3 (if applicable), the value of a Covid Variation shall as far as possible be valued by agreement between the Contractor and the Engineer. Failing agreement, the value shall be determined by the Engineer in accordance with 9.3.

## Slide 19
Be part of the Accord and keep up-to-date on progress at
www.constructionaccord.nz

## Slide 20: Covid, Delta and Omicron – Contractors View

## Slide 21: State of Contracts – Mixed Bag
Pre Covid-Contracts still being worked on.
Post March 20 - Contracts that refer to :
  various levels of Lockdown.
  traffic lights
  Govt restrictions.
Government have a more project friendly position
Commercial contracts – more focussed on the $$ and who wears the costs.
Generally clear who bears the risk.
Still plenty of variances and always worth tagging at tender stage.
Variable relief:
  Time & Costs – full or partial
  Some give escalation relief
  Onsite costs only
  Time only
  No relief

## Slide 22: What to do if you’ve been impacted?
Check your Contract.
Determine how and what has been impacted.
Check your contract.
What relief is available?
Collate your records – staff/worker numbers, materials impacted, programme up to date?
Don’t be a postbox on Costs or supply chain costs
Get a notice out as soon as possible – either early warning or notice of delay.

## Slide 23: Types of entitlement
Costs incurred but no impact on critical path
  Check your contract
  A Variation may still have occurred (deemed Variation)
  What notices and information do you need to comply with.
  Calculate the costs incurred in line with the Contract.
  Due your due diligence on supply chain costs
Programme and Cost impact.
  Check your contract.
  What notices and information do you need to comply with.
  Has critical path been affected.
  Is your programme up to date.
  Demonstrate impact
  Track impacted activities
  Track trade specific site numbers – before and after the events
  Put your notices in
  Calculate costs incurred in line with Contract.
  Do your due diligence on supply chain data

## Slide 24: Subcontractors and Covid
  Some Clients, EtCs, Client QS – don’t seem to think that Subs have an entitlement,
  Head Contract:
    Does it exclude Subcontractors costs?
    If not, then claim in accordance with the Contract
  Subcontract:
    Check what you have contracted the supply chain to:
    May be conflicted to the Head contract position
Carry out due diligence on supply chain claims before presenting.

## Slide 25: Current view of entitlement
Go to the top of the tree for dialogue.
Current EtC/ EtC reps view of entitlement
  Still mixed – client’s interest or projects interest.
  Strange view on definition of costs
    ‘standard variation’ – no problem
    ‘Covid Variation’ – Costs are not the same
  Tending to negotiate on behalf of client rather than applying the Contract
Consultant QS
  Generally, best not to engage with them on Covid
Direct engagement with Clients
  Direct engagement may be best option.
Haven't heard of a Covid claim going beyond the Contract yet.

## Slide 26: What's Next?
Material ordering earlier and earlier.
Clients paying for offsite as soon as its available & paying deposits.
Off-site storage facilities
Covid/Omicron impacts will be here for a while.
Potential ways of dealing with it:
  Contractor takes a view in programme and costs – similar to wet weather?
  Govt takes less of an interest, and it becomes an industry issue?

## Slide 27
Questions?
Next Presenter

## Slide 29
Extensions of Time in the Omicron Environment
Engineer’s Perspective
06 April 2022
Graham Stanage

## Slide 30: KEY PRINCIPLES
Know your Contract – in particular its “Special Conditions”
Understand what is giving grounds for the claim
A change has occurred that has influenced the Contractor’s ability to deliver
  Effect on time
  Effect on cost
  Evidence of the effects can be presented
Inform the Engineer & Principal (NoD)
Prepare claims thoroughly

## Slide 31
PRESENT –
OMICRON ENVIRONMENT
Delay & Disruption
through -
  Resource availability
    Labour
    Materials
    Plant
  Inefficiency

## Slide 32: NOTIFICATION OF DELAY (NoD)
Notice should be given as early as possible.
There must be a measurable delay – it needs a base date as to when things should have happened.
Must have sufficient detail to allow the Engineer to understand and identify the cause of the delay.
The NoD should say what provisions under the contract it is notified.
The NoD should say which activities / trades are delayed or consequentially affected.
The NoD should say what mitigations (if any) have been taken are recommended or possible.

## Slide 33: BEFORE AN EOT CLAIM IS ISSUED
Understand your contract – both the Principal’s and Contractor’s obligations.
In particular, be familiar with Covid event provisions
Understand the allocation of risk under the contract.
Understand the EOT claim process under the Contract and whether these have been followed.
Understand the programme, its critical path activities, logic dependencies, sequencing of works through to Practical Completion.
Understand the status of the programme being used to justify the claim.

## Slide 34: BEFORE DECIDING TO MAKE AN EOT CLAIM
Was the effect of the delay mitigated? – advise what measures were taken.
Check if there were any concurrent delays for which the Contractor may be responsible that may have contributed to the delay in completion.
Understand the impact of the delay on Sub-Contractors and suppliers - provide backup documentation to support the full claim.
EOT Essential elements/ Check Lists - review

## Slide 35: PROGRAMME FUNDAMENTALS – to allow for accurate assessment
The programme must be in sufficient detail that progress can be measured.
The programme should demonstrate a clear critical path.
The programme must be regularly updated and reflect current progress.
The programme should highlight constraints between activities.
The programme should have measurable outcomes/ milestones.

## Slide 36: KEY ACTIONS / PROCESS FOR ENGINEER
On receipt of EOT:
  Check if notice of delay was given.
  Check what critical activities were claimed to be delayed.
  Check what subsequent activities would be affected and whether they were delayed to the same extent.
  Check if there was any float in the programme or ability to re-sequence the works.
  Undertake detailed review of records and documentation to support the claim.

## Slide 37: KEY ACTIONS FOR ENGINEER TO CONTRACT
On receipt of EOT:
  Jointly examine opportunities to mitigate the delay.
  Consider if acceleration is an alternative to an EOT.
  Engineer to independently assess the claim taking into account statements and other evidence provided by the Contractor.
  The Engineer to the Contract should then issue an EOT adjusting the Due Date for Completion of the Works
  The Principal and Contractor have the right to dispute the Engineer’s assessment of the claim.

## Slide 38: KEY CONSIDERATIONS FOR ENGINEER
Has actual delay to the Due Date for Completion occurred?
Can delay be demonstrated against the most recent programme?
Concurrency of delay…
Time
Costs associated with delay
  Direct costs
  Indirect Costs
  Sub-contractor costs
Off-site Overheads and Profit

## Slide 39: KEY CONSIDERATIONS FOR ENGINEER
Inefficiency – how to measure
Absenteeism
  Staff
  Labour/ Subcontractors
Material Shortages
Measured mile
Cash flow comparison
Ongoing delay
Records

## Slide 40
Graham Stanage
Director
gstanage@rcp.co.nz
021 782 643